## 12-Week Plan
Week | Workstream | Task Title | Detailed Task | Owner Role | Inputs | Outputs/Deliverables | Success Metric | Status
1 | Governance | Kick-off & scope lock | Confirm SKUs in scope (bagasse, paper bowls, paper cups, CPLA); assign RACI; set milestones to 2026-08-12 and 2028-08-12. | Compliance Lead | SKU list; sales forecast | Project charter; RACI; timeline | Sign-off by GM
1 | Data | SKU master audit | Map current master data to PPWR fields (materials, coatings, inks, adhesives). | PLM Manager | ERP/PLM export | Gap list | 100% SKUs mapped
1 | Legal | Requirement register | Create PPWR requirement register (DfR grades, compostability exceptions, labelling, recycled content, reuse). | Regulatory Counsel | PPWR text/briefs | Requirement matrix | Reviewed by Compliance
2 | Supplier | Supplier request pack | Issue standardised request for: composition declarations, DoC, migration tests, PCR chain-of-custody, recyclability evidence, ink/adhesive specs. | Sourcing Manager | Supplier list | RFIs sent | 100% Tier-1 sent
2 | Risk | Risk baseline | Score SKUs by risk (multi-material, non-separable layers, high-oil/acid contact, hot-fill, complex lids). | Quality Manager | SKU audit; test history | Risk heatmap | Top 20% risk identified
3 | Supplier | Evidence intake | Collect supplier files; track completeness & validity (dates, standards). | Sourcing Manager | Supplier returns | Evidence tracker | >60% on-time returns
3 | Engineering | Quick DfR fixes (wave 1) | Remove design blockers: labels/inks that hinder recycling; switch to separable components; reduce composite layers. | Packaging Engineer | Risk heatmap | ECN list (wave 1) | ≥10 SKUs fixed
4 | Lab | Targeted tests | Run migration, oil/acid resistance, drop/leak tests; validate temperature windows (microwave vs steam). | Lab Lead | Test protocols | Test reports | 100% high-risk SKUs tested
4 | EPR | EPR scoping | Identify Member States to register, schemes, fee categories, reporting frequency; estimate 12-month eco-fee budget. | Finance Controller | Sales by country | EPR map + budget | Finance sign-off
5 | Label | Harmonised label master | Draft material composition icons + sorting instructions; create 27-language label master with placeholders. | Brand Design Lead | Label guidelines | Label artwork v0.9 | Pre-approval by Legal
5 | Data | PCR traceability setup | Define evidence chain (supplier certificate + invoices + batch trace) for PCR. | Compliance Lead | Supplier PCR docs | PCR SOP | SOP approved
6 | Documentation | Technical file template | Assemble DoC template, test index, DfR worksheet, recyclability grade rationale, EPR proof placeholders. | QA Documentation | Requirement register | Tech file v1.0 | Template frozen
6 | Engineering | Quick DfR fixes (wave 2) | Address lids/fit tolerances, low-migration inks/adhesives. | Packaging Engineer | Test data | ECN list (wave 2) | ≥20 SKUs at target
7 | EPR | Scheme registrations | Submit producer registrations in priority Member States; prepare first reporting templates. | EPR Specialist | EPR map | Registration IDs | ≥5 key MS registered
7 | Operations | Artwork changeover plan | Plan print plates, MOQs, old stock run-out, relabelling contingencies. | Ops Planner | Inventory levels | Changeover Gantt | No stockouts
8 | Pilot | Pilot market launch | Launch 3–5 SKUs with new structures/labels; monitor defect/leakage in distribution. | Sales Ops | Customer partners | Pilot report | KPIs ≥ baseline
9 | Documentation | Tech files completed | Populate SKU files with supplier docs, tests, label proofs, EPR IDs. | QA Documentation | Collected evidence | Tech file set | 100% priority SKUs done
9 | Finance | Eco-fee accruals | Load fee modulation assumptions by recyclability grade; set quarterly accruals. | Finance Controller | Scheme fee tables | Accrual model | Controller sign-off
10 | Engineering | Design freeze | Freeze A/B/C designs for new POs; block D/E grade items from launch. | CTO | DfR worksheets | Design freeze notice | POs only A/B/C
11 | IT/PLM | Master data fields | Add PPWR fields to ERP/PLM (grade, PCR, label code, EPR IDs). | IT Owner | Field schema | PLM update | 100% fields live
11 | Training | Enablement | Train Sales/CS on claims, labels, market differences. | Compliance Lead | Training deck | Sessions complete | >90% pass quiz
12 | Audit | Internal audit | Run readiness audit; fix gaps; sign launch memo. | Internal Audit | Tech files; SOPs | Audit report | No major findings
12 | Launch | General release | Approve rollout to EU customers for compliant SKUs; set monitoring cadence. | GM/VP Ops | Audit sign-off | Go-live | On-time launch

## File Pack Fields
Field Name | Description | Data Type | Owner | Applies To | Mandatory | Example/Allowed Values
SKU_ID | Unique SKU identifier | text | PLM | All | Y | BOWL-16OZ-KP-PLA
Product_Name | Marketing name / size | text | Marketing | All | Y | 16oz Kraft Paper Salad Bowl
Category | Product category | enum | PLM | All | Y | Bagasse¦Paper Bowl¦Paper Cup¦CPLA¦Lid
Variant | Color/finish/print | enum | PLM | All | Y | white¦kraft¦printed¦clear¦black
Food_Contact | Intended food contact (yes/no) | enum | Regulatory | All | Y | yes¦no
Intended_Use | Use conditions (hot/cold, microwave/steam, oil/acid) | enum | Regulatory | All | Y | hot¦cold¦microwave¦steam¦oil¦acid
Primary_Material | Main substrate | enum | Engineering | All | Y | bagasse¦paper¦CPLA¦PLA¦PP¦PET
Coating/Barrier | Coating material / gsm / side(s) | text | Engineering | Paper/Bowls/Cups | C | PLA 25gsm single-side
Adhesives_Type | Adhesive chemistry and location | text | Engineering | All | C | water-based acrylic; rim seam
Inks_System | Printing ink system (low-migration), % coverage | text | Engineering | Printed SKUs | C | water-based flexo, 2 colors, 35% coverage
Separable_Components | Can layers/components be separated for recycling | enum | Engineering | All | Y | yes¦no
DfR_Target_Grade | Target recyclability grade A/B/C | enum | Engineering | All | Y | A¦B¦C
DfR_Blockers | Known design incompatibilities (labels, inks, barriers) | text | Engineering | All | C | non-separable laminate; metallic ink
Recyclability_Rationale | Evidence/logic for grade (test, guidelines) | text | Regulatory | All | Y | RecyClass method; supplier test report ID
Recycled_Content_% | Post-consumer recycled content in plastic parts | number | Regulatory | Plastic parts | C | 30
Compostable_App | Falls under mandatory compostable items | enum | Regulatory | Specific items | C | tea/coffee bag¦fruit sticker¦very light plastic bag¦N/A
Compost_Standard | Standard (EN 13432 / ASTM D6400) | enum | Regulatory | Compostables | C | EN 13432¦ASTM D6400¦N/A
Reuse_System | Participates in reuse/refill system | enum | Business | Reusable SKUs | C | yes¦no
Min_Rotations | Minimum rotations (once defined) | number | Business | Reusable SKUs | C | 25
Label_Material_Code | Material composition icon code | text | Design | All | Y | PAPER-CARD
Sorting_Instructions | Consumer sorting text (EU harmonised) | text | Design | All | Y | Dispose in paper bin (local rules apply)
Languages | Languages on artwork | text | Design | All | Y | EN, FR, DE, ES, IT, NL, PT, PL, ...
DoC_ID | Declaration of Compliance identifier | text | Regulatory | Food-contact | Y | DOC-2025-001
Migration_Test_Ref | Global/specific migration test reference | text | Lab | Food-contact | C | EN 1186 overall; simulant D2 40°C/10d
Temperature_Window | Validated operating range | text | Lab | All | C | 0–100°C; microwave safe 3 min at 800W
EPR_Country | Member State of registration | enum | EPR | EU sales | Y | DE¦FR¦IT¦ES¦NL¦...
EPR_Registration_ID | Producer registration number | text | EPR | EU sales | Y | DE-123456-PACK
EPR_Category | Fee category (material/format) | text | EPR | EU sales | Y | paper; plastic; composite
Reporting_Frequency | EPR reporting cadence | enum | EPR | EU sales | Y | monthly¦quarterly¦annual
Environmental_Claims | Approved on-pack claims text | text | Legal | All | Y | Designed for recycling; do not claim biodegradable
ECN_ID | Engineering change notice ID | text | Engineering | All | Y | ECN-2025-045
Effective_Date | Effective date of change | date | Engineering | All | Y | 2026-03-01

## Sample SKUs
SKU_ID | Category | Product_Name | Variant | Food_Contact | Intended_Use | Primary_Material | Coating/Barrier | Separable_Components | DfR_Target_Grade | Recyclability_Rationale | Recycled_Content_% | Compostable_App | Compost_Standard | Reuse_System | Min_Rotations | Label_Material_Code | Sorting_Instructions | Languages | DoC_ID | Migration_Test_Ref | Temperature_Window | EPR_Country | EPR_Registration_ID | EPR_Category | Reporting_Frequency | Environmental_Claims | ECN_ID | Effective_Date
BAG-CLAM-8X8-3C | Bagasse Molded Fiber | 8x8 3-Compartment Clamshell | white | yes | hot,oil | bagasse | N/A | yes | B | Molded fiber mono-material; aligns with paper stream |  | N/A | N/A |  |  | PAPER-FIBRE | Dispose in paper bin (local rules apply) | EN,DE,FR,IT,ES,NL,PL | DOC-2025-101 | EN 1186; D2 40°C/10d | 0–100°C; microwave 3 min/800W | DE | DE-123456-PACK | paper | quarterly | Designed for recycling | ECN-2025-010 | 2026-03-01
BAG-PLATE-9R | Bagasse Molded Fiber | 9" Round Plate | white | yes | hot,oil,acid | bagasse | N/A | yes | A | Mono-material molded fiber; no barrier |  | N/A | N/A |  |  | PAPER-FIBRE | Dispose in paper bin | EN,FR,ES | DOC-2025-102 | EN 1186; B 70°C/2h | 0–100°C | FR | FR-987654-PACK | paper | annual | Designed for recycling | ECN-2025-012 | 2026-03-15
BAG-SAUCE-2OZ | Bagasse Molded Fiber | 2oz Sauce Cup | white | yes | hot,oil,acid | bagasse | N/A | yes | A | Mono-material molded fiber |  | N/A | N/A |  |  | PAPER-FIBRE | Dispose in paper bin | EN,ES | DOC-2025-103 | EN 1186; D2 40°C/10d | 0–100°C | ES | ES-776655-PACK | paper | quarterly | Designed for recycling | ECN-2025-013 | 2026-04-01
PAP-BOWL-16OZ-KR-PLA | Paper Bowl | 16oz Kraft Paper Bowl | kraft | yes | hot,oil,microwave | paper | PLA 25gsm single-side | yes | C | Paper with separable bio-based coating; target C pending implementing acts |  | N/A | N/A |  |  | PAPER-CARD | Dispose in paper bin (local rules apply) | EN,IT,DE | DOC-2025-201 | EN 1186; D2 40°C/10d | 0–100°C; microwave 3 min/800W | IT | IT-889900-PACK | paper | quarterly | Designed for recycling | ECN-2025-020 | 2026-05-01
PAP-BOWL-24OZ-WH-PE | Paper Bowl | 24oz White Paper Bowl | white | yes | hot,oil,steam | paper | PE 18gsm single-side | yes | C | Paper dominant with low-gsm barrier; separability under test |  | N/A | N/A |  |  | PAPER-CARD | Dispose in paper bin (local rules apply) | EN,ES,PL | DOC-2025-202 | EN 1186; D2 40°C/10d | 0–100°C; steam exposure validated | ES | ES-776655-PACK | paper | annual | Designed for recycling | ECN-2025-021 | 2026-05-15
PAP-BOWL-32OZ-KR-PLA | Paper Bowl | 32oz Kraft Paper Bowl | kraft | yes | hot,oil,steam | paper | PLA 25gsm single-side | yes | C | Separable barrier |  | N/A | N/A |  |  | PAPER-CARD | Dispose in paper bin | EN,NL | DOC-2025-203 | EN 1186; D2 40°C/10d | 0–100°C | NL | NL-445566-PACK | paper | quarterly | Designed for recycling | ECN-2025-022 | 2026-06-01
PAP-CUP-8OZ-SW-PLA | Paper Cup | 8oz Single Wall Cup | white | yes | hot | paper | PLA 20gsm single-side | yes | C | Paper with bio-barrier; C-grade target per guidance |  | N/A | N/A |  |  | PAPER-CARD | Dispose in paper bin | EN,NL,PT | DOC-2025-301 | EN 1186; B 70°C/2h | 0–90°C | NL | NL-445566-PACK | paper | quarterly | Designed for recycling | ECN-2025-030 | 2026-04-01
PAP-CUP-12OZ-DW-PE | Paper Cup | 12oz Double Wall Cup | kraft | yes | hot,oil | paper | PE 20gsm single-side | yes | B | Paper outer + separable liner; improved recovery potential |  | N/A | N/A |  |  | PAPER-CARD | Dispose in paper bin | EN,SE | DOC-2025-302 | EN 1186; D2 40°C/10d | 0–90°C | SE | SE-998877-PACK | paper | annual | Designed for recycling | ECN-2025-031 | 2026-04-15
PAP-CUP-16OZ-SW-PE | Paper Cup | 16oz Single Wall Cup | white | yes | cold | paper | PE 18gsm single-side | yes | C | Separable liner |  | N/A | N/A |  |  | PAPER-CARD | Dispose in paper bin | EN,PL | DOC-2025-303 | EN 1186; simulants A/B | 0–60°C | PL | PL-221133-PACK | paper | quarterly | Designed for recycling | ECN-2025-032 | 2026-05-01
CPLA-FORK-165MM-WH | CPLA Cutlery | 165mm CPLA Fork | white | yes | hot,oil | CPLA | N/A | yes | C | CPLA stream; verify local capabilities |  | N/A | N/A |  |  | PLASTIC-CPLA | Dispose per local rules | EN,PT | DOC-2025-401 | EU 10/2011 (screen) | -10–80°C | PT | PT-661122-PACK | plastic | annual | Designed for recycling | ECN-2025-040 | 2026-06-15
CPLA-SPOON-165MM-BK | CPLA Cutlery | 165mm CPLA Spoon | black | yes | hot,oil | CPLA | N/A | yes | C | CPLA stream |  | N/A | N/A |  |  | PLASTIC-CPLA | Dispose per local rules | EN,ES | DOC-2025-402 | EU 10/2011 (screen) | -10–80°C | ES | ES-112233-PACK | plastic | annual | Designed for recycling | ECN-2025-041 | 2026-06-20
CPLA-KNIFE-170MM-WH | CPLA Cutlery | 170mm CPLA Knife | white | yes | hot | CPLA | N/A | yes | C | CPLA stream |  | N/A | N/A |  |  | PLASTIC-CPLA | Dispose per local rules | EN,SV | DOC-2025-403 | EU 10/2011 (screen) | -10–80°C | SE | SE-998877-PACK | plastic | annual | Designed for recycling | ECN-2025-042 | 2026-06-25
LID-PP-115MM-CLR | Lid | 115mm PP Lid (Clear) | clear | yes | cold | PP | N/A | yes | B | Mono PP | 10 | N/A | N/A |  |  | PLASTIC-PP | Dispose per plastics bin | EN,DE | DOC-2025-501 | EU 10/2011 overall | -10–60°C | DE | DE-123456-PACK | plastic | quarterly | Contains 10% PCR | ECN-2025-050 | 2026-07-01
LID-CPLA-115MM-WH | Lid | 115mm CPLA Lid (White) | white | yes | hot | CPLA | N/A | yes | C | CPLA stream; check local capabilities |  | N/A | N/A |  |  | PLASTIC-CPLA | Dispose per local rules | EN,FR | DOC-2025-502 | EU 10/2011 overall | -10–80°C | FR | FR-987654-PACK | plastic | annual | Designed for recycling | ECN-2025-051 | 2026-07-10
PAP-BOWL-6OZ-WH-PLA | Paper Bowl | 6OZ White Paper Bowl | white | yes | hot,oil | paper | PLA 20gsm single-side | yes | C | Paper with separable bio-barrier |  | N/A | N/A |  |  | PAPER-CARD | Dispose in paper bin | EN,IT,DE | DOC-2025-2XX | EN 1186; D2 40°C/10d | 0–100°C | IT | IT-889900-PACK | paper | quarterly | Designed for recycling | ECN-2025-02X | 2026-05-01
PAP-BOWL-12OZ-WH-PLA | Paper Bowl | 12OZ White Paper Bowl | white | yes | hot,oil | paper | PLA 20gsm single-side | yes | C | Paper with separable bio-barrier |  | N/A | N/A |  |  | PAPER-CARD | Dispose in paper bin | EN,IT,DE | DOC-2025-2XX | EN 1186; D2 40°C/10d | 0–100°C | IT | IT-889900-PACK | paper | quarterly | Designed for recycling | ECN-2025-02X | 2026-05-01
PAP-BOWL-20OZ-WH-PLA | Paper Bowl | 20OZ White Paper Bowl | white | yes | hot,oil | paper | PLA 20gsm single-side | yes | C | Paper with separable bio-barrier |  | N/A | N/A |  |  | PAPER-CARD | Dispose in paper bin | EN,IT,DE | DOC-2025-2XX | EN 1186; D2 40°C/10d | 0–100°C | IT | IT-889900-PACK | paper | quarterly | Designed for recycling | ECN-2025-02X | 2026-05-01
PAP-CUP-7OZ-SW-PLA | Paper Cup | 7OZ Single Wall Cup | white | yes | hot | paper | PLA 20gsm single-side | yes | C | Paper with bio-barrier |  | N/A | N/A |  |  | PAPER-CARD | Dispose in paper bin | EN,NL,PT | DOC-2025-3XX | EN 1186; B 70°C/2h | 0–90°C | NL | NL-445566-PACK | paper | quarterly | Designed for recycling | ECN-2025-03X | 2026-04-01
PAP-CUP-10OZ-SW-PLA | Paper Cup | 10OZ Single Wall Cup | white | yes | hot | paper | PLA 20gsm single-side | yes | C | Paper with bio-barrier |  | N/A | N/A |  |  | PAPER-CARD | Dispose in paper bin | EN,NL,PT | DOC-2025-3XX | EN 1186; B 70°C/2h | 0–90°C | NL | NL-445566-PACK | paper | quarterly | Designed for recycling | ECN-2025-03X | 2026-04-01
PAP-CUP-20OZ-SW-PLA | Paper Cup | 20OZ Single Wall Cup | white | yes | hot | paper | PLA 20gsm single-side | yes | C | Paper with bio-barrier |  | N/A | N/A |  |  | PAPER-CARD | Dispose in paper bin | EN,NL,PT | DOC-2025-3XX | EN 1186; B 70°C/2h | 0–90°C | NL | NL-445566-PACK | paper | quarterly | Designed for recycling | ECN-2025-03X | 2026-04-01

## Label Master
Label_Material_Code | Language | Sorting_Text_Placeholder | Icon_Ref | Version
PAPER-CARD | EN | Dispose in paper bin (local rules apply) | PAPER-CARD-ICON | v0.9
PAPER-CARD | FR | Dispose in paper bin (local rules apply) | PAPER-CARD-ICON | v0.9
PAPER-CARD | DE | Dispose in paper bin (local rules apply) | PAPER-CARD-ICON | v0.9
PAPER-CARD | ES | Dispose in paper bin (local rules apply) | PAPER-CARD-ICON | v0.9
PAPER-CARD | IT | Dispose in paper bin (local rules apply) | PAPER-CARD-ICON | v0.9
PAPER-CARD | NL | Dispose in paper bin (local rules apply) | PAPER-CARD-ICON | v0.9
PAPER-CARD | PL | Dispose in paper bin (local rules apply) | PAPER-CARD-ICON | v0.9
PAPER-CARD | PT | Dispose in paper bin (local rules apply) | PAPER-CARD-ICON | v0.9
PAPER-CARD | SE | Dispose in paper bin (local rules apply) | PAPER-CARD-ICON | v0.9
PAPER-CARD | FI | Dispose in paper bin (local rules apply) | PAPER-CARD-ICON | v0.9
PAPER-CARD | DA | Dispose in paper bin (local rules apply) | PAPER-CARD-ICON | v0.9
PAPER-CARD | NO | Dispose in paper bin (local rules apply) | PAPER-CARD-ICON | v0.9
PAPER-CARD | CS | Dispose in paper bin (local rules apply) | PAPER-CARD-ICON | v0.9
PAPER-CARD | SK | Dispose in paper bin (local rules apply) | PAPER-CARD-ICON | v0.9
PAPER-CARD | SL | Dispose in paper bin (local rules apply) | PAPER-CARD-ICON | v0.9
PAPER-CARD | HU | Dispose in paper bin (local rules apply) | PAPER-CARD-ICON | v0.9
PAPER-CARD | RO | Dispose in paper bin (local rules apply) | PAPER-CARD-ICON | v0.9
PAPER-CARD | BG | Dispose in paper bin (local rules apply) | PAPER-CARD-ICON | v0.9
PAPER-CARD | EL | Dispose in paper bin (local rules apply) | PAPER-CARD-ICON | v0.9
PAPER-CARD | HR | Dispose in paper bin (local rules apply) | PAPER-CARD-ICON | v0.9
PAPER-CARD | LT | Dispose in paper bin (local rules apply) | PAPER-CARD-ICON | v0.9
PAPER-CARD | LV | Dispose in paper bin (local rules apply) | PAPER-CARD-ICON | v0.9
PAPER-CARD | ET | Dispose in paper bin (local rules apply) | PAPER-CARD-ICON | v0.9
PAPER-CARD | MT | Dispose in paper bin (local rules apply) | PAPER-CARD-ICON | v0.9
PAPER-CARD | GA | Dispose in paper bin (local rules apply) | PAPER-CARD-ICON | v0.9
PAPER-CARD | SV | Dispose in paper bin (local rules apply) | PAPER-CARD-ICON | v0.9
PAPER-CARD | PT-BR | Dispose in paper bin (local rules apply) | PAPER-CARD-ICON | v0.9
PAPER-FIBRE | EN | Dispose in paper bin (local rules apply) | PAPER-FIBRE-ICON | v0.9
PAPER-FIBRE | FR | Dispose in paper bin (local rules apply) | PAPER-FIBRE-ICON | v0.9
PAPER-FIBRE | DE | Dispose in paper bin (local rules apply) | PAPER-FIBRE-ICON | v0.9
PAPER-FIBRE | ES | Dispose in paper bin (local rules apply) | PAPER-FIBRE-ICON | v0.9
PAPER-FIBRE | IT | Dispose in paper bin (local rules apply) | PAPER-FIBRE-ICON | v0.9
PAPER-FIBRE | NL | Dispose in paper bin (local rules apply) | PAPER-FIBRE-ICON | v0.9
PAPER-FIBRE | PL | Dispose in paper bin (local rules apply) | PAPER-FIBRE-ICON | v0.9
PAPER-FIBRE | PT | Dispose in paper bin (local rules apply) | PAPER-FIBRE-ICON | v0.9
PAPER-FIBRE | SE | Dispose in paper bin (local rules apply) | PAPER-FIBRE-ICON | v0.9
PAPER-FIBRE | FI | Dispose in paper bin (local rules apply) | PAPER-FIBRE-ICON | v0.9
PAPER-FIBRE | DA | Dispose in paper bin (local rules apply) | PAPER-FIBRE-ICON | v0.9
PAPER-FIBRE | NO | Dispose in paper bin (local rules apply) | PAPER-FIBRE-ICON | v0.9
PAPER-FIBRE | CS | Dispose in paper bin (local rules apply) | PAPER-FIBRE-ICON | v0.9
PAPER-FIBRE | SK | Dispose in paper bin (local rules apply) | PAPER-FIBRE-ICON | v0.9
PAPER-FIBRE | SL | Dispose in paper bin (local rules apply) | PAPER-FIBRE-ICON | v0.9
PAPER-FIBRE | HU | Dispose in paper bin (local rules apply) | PAPER-FIBRE-ICON | v0.9
PAPER-FIBRE | RO | Dispose in paper bin (local rules apply) | PAPER-FIBRE-ICON | v0.9
PAPER-FIBRE | BG | Dispose in paper bin (local rules apply) | PAPER-FIBRE-ICON | v0.9
PAPER-FIBRE | EL | Dispose in paper bin (local rules apply) | PAPER-FIBRE-ICON | v0.9
PAPER-FIBRE | HR | Dispose in paper bin (local rules apply) | PAPER-FIBRE-ICON | v0.9
PAPER-FIBRE | LT | Dispose in paper bin (local rules apply) | PAPER-FIBRE-ICON | v0.9
PAPER-FIBRE | LV | Dispose in paper bin (local rules apply) | PAPER-FIBRE-ICON | v0.9
PAPER-FIBRE | ET | Dispose in paper bin (local rules apply) | PAPER-FIBRE-ICON | v0.9
PAPER-FIBRE | MT | Dispose in paper bin (local rules apply) | PAPER-FIBRE-ICON | v0.9
PAPER-FIBRE | GA | Dispose in paper bin (local rules apply) | PAPER-FIBRE-ICON | v0.9
PAPER-FIBRE | SV | Dispose in paper bin (local rules apply) | PAPER-FIBRE-ICON | v0.9
PAPER-FIBRE | PT-BR | Dispose in paper bin (local rules apply) | PAPER-FIBRE-ICON | v0.9
PLASTIC-PP | EN | Dispose per local rules | PLASTIC-PP-ICON | v0.9
PLASTIC-PP | FR | Dispose per local rules | PLASTIC-PP-ICON | v0.9
PLASTIC-PP | DE | Dispose per local rules | PLASTIC-PP-ICON | v0.9
PLASTIC-PP | ES | Dispose per local rules | PLASTIC-PP-ICON | v0.9
PLASTIC-PP | IT | Dispose per local rules | PLASTIC-PP-ICON | v0.9
PLASTIC-PP | NL | Dispose per local rules | PLASTIC-PP-ICON | v0.9
PLASTIC-PP | PL | Dispose per local rules | PLASTIC-PP-ICON | v0.9
PLASTIC-PP | PT | Dispose per local rules | PLASTIC-PP-ICON | v0.9
PLASTIC-PP | SE | Dispose per local rules | PLASTIC-PP-ICON | v0.9
PLASTIC-PP | FI | Dispose per local rules | PLASTIC-PP-ICON | v0.9
PLASTIC-PP | DA | Dispose per local rules | PLASTIC-PP-ICON | v0.9
PLASTIC-PP | NO | Dispose per local rules | PLASTIC-PP-ICON | v0.9
PLASTIC-PP | CS | Dispose per local rules | PLASTIC-PP-ICON | v0.9
PLASTIC-PP | SK | Dispose per local rules | PLASTIC-PP-ICON | v0.9
PLASTIC-PP | SL | Dispose per local rules | PLASTIC-PP-ICON | v0.9
PLASTIC-PP | HU | Dispose per local rules | PLASTIC-PP-ICON | v0.9
PLASTIC-PP | RO | Dispose per local rules | PLASTIC-PP-ICON | v0.9
PLASTIC-PP | BG | Dispose per local rules | PLASTIC-PP-ICON | v0.9
PLASTIC-PP | EL | Dispose per local rules | PLASTIC-PP-ICON | v0.9
PLASTIC-PP | HR | Dispose per local rules | PLASTIC-PP-ICON | v0.9
PLASTIC-PP | LT | Dispose per local rules | PLASTIC-PP-ICON | v0.9
PLASTIC-PP | LV | Dispose per local rules | PLASTIC-PP-ICON | v0.9
PLASTIC-PP | ET | Dispose per local rules | PLASTIC-PP-ICON | v0.9
PLASTIC-PP | MT | Dispose per local rules | PLASTIC-PP-ICON | v0.9
PLASTIC-PP | GA | Dispose per local rules | PLASTIC-PP-ICON | v0.9
PLASTIC-PP | SV | Dispose per local rules | PLASTIC-PP-ICON | v0.9
PLASTIC-PP | PT-BR | Dispose per local rules | PLASTIC-PP-ICON | v0.9
PLASTIC-PET | EN | Dispose per local rules | PLASTIC-PET-ICON | v0.9
PLASTIC-PET | FR | Dispose per local rules | PLASTIC-PET-ICON | v0.9
PLASTIC-PET | DE | Dispose per local rules | PLASTIC-PET-ICON | v0.9
PLASTIC-PET | ES | Dispose per local rules | PLASTIC-PET-ICON | v0.9
PLASTIC-PET | IT | Dispose per local rules | PLASTIC-PET-ICON | v0.9
PLASTIC-PET | NL | Dispose per local rules | PLASTIC-PET-ICON | v0.9
PLASTIC-PET | PL | Dispose per local rules | PLASTIC-PET-ICON | v0.9
PLASTIC-PET | PT | Dispose per local rules | PLASTIC-PET-ICON | v0.9
PLASTIC-PET | SE | Dispose per local rules | PLASTIC-PET-ICON | v0.9
PLASTIC-PET | FI | Dispose per local rules | PLASTIC-PET-ICON | v0.9
PLASTIC-PET | DA | Dispose per local rules | PLASTIC-PET-ICON | v0.9
PLASTIC-PET | NO | Dispose per local rules | PLASTIC-PET-ICON | v0.9
PLASTIC-PET | CS | Dispose per local rules | PLASTIC-PET-ICON | v0.9
PLASTIC-PET | SK | Dispose per local rules | PLASTIC-PET-ICON | v0.9
PLASTIC-PET | SL | Dispose per local rules | PLASTIC-PET-ICON | v0.9
PLASTIC-PET | HU | Dispose per local rules | PLASTIC-PET-ICON | v0.9
PLASTIC-PET | RO | Dispose per local rules | PLASTIC-PET-ICON | v0.9
PLASTIC-PET | BG | Dispose per local rules | PLASTIC-PET-ICON | v0.9
PLASTIC-PET | EL | Dispose per local rules | PLASTIC-PET-ICON | v0.9
PLASTIC-PET | HR | Dispose per local rules | PLASTIC-PET-ICON | v0.9
PLASTIC-PET | LT | Dispose per local rules | PLASTIC-PET-ICON | v0.9
PLASTIC-PET | LV | Dispose per local rules | PLASTIC-PET-ICON | v0.9
PLASTIC-PET | ET | Dispose per local rules | PLASTIC-PET-ICON | v0.9
PLASTIC-PET | MT | Dispose per local rules | PLASTIC-PET-ICON | v0.9
PLASTIC-PET | GA | Dispose per local rules | PLASTIC-PET-ICON | v0.9
PLASTIC-PET | SV | Dispose per local rules | PLASTIC-PET-ICON | v0.9
PLASTIC-PET | PT-BR | Dispose per local rules | PLASTIC-PET-ICON | v0.9
PLASTIC-CPLA | EN | Dispose per local rules | PLASTIC-CPLA-ICON | v0.9
PLASTIC-CPLA | FR | Dispose per local rules | PLASTIC-CPLA-ICON | v0.9
PLASTIC-CPLA | DE | Dispose per local rules | PLASTIC-CPLA-ICON | v0.9
PLASTIC-CPLA | ES | Dispose per local rules | PLASTIC-CPLA-ICON | v0.9
PLASTIC-CPLA | IT | Dispose per local rules | PLASTIC-CPLA-ICON | v0.9
PLASTIC-CPLA | NL | Dispose per local rules | PLASTIC-CPLA-ICON | v0.9
PLASTIC-CPLA | PL | Dispose per local rules | PLASTIC-CPLA-ICON | v0.9
PLASTIC-CPLA | PT | Dispose per local rules | PLASTIC-CPLA-ICON | v0.9
PLASTIC-CPLA | SE | Dispose per local rules | PLASTIC-CPLA-ICON | v0.9
PLASTIC-CPLA | FI | Dispose per local rules | PLASTIC-CPLA-ICON | v0.9
PLASTIC-CPLA | DA | Dispose per local rules | PLASTIC-CPLA-ICON | v0.9
PLASTIC-CPLA | NO | Dispose per local rules | PLASTIC-CPLA-ICON | v0.9
PLASTIC-CPLA | CS | Dispose per local rules | PLASTIC-CPLA-ICON | v0.9
PLASTIC-CPLA | SK | Dispose per local rules | PLASTIC-CPLA-ICON | v0.9
PLASTIC-CPLA | SL | Dispose per local rules | PLASTIC-CPLA-ICON | v0.9
PLASTIC-CPLA | HU | Dispose per local rules | PLASTIC-CPLA-ICON | v0.9
PLASTIC-CPLA | RO | Dispose per local rules | PLASTIC-CPLA-ICON | v0.9
PLASTIC-CPLA | BG | Dispose per local rules | PLASTIC-CPLA-ICON | v0.9
PLASTIC-CPLA | EL | Dispose per local rules | PLASTIC-CPLA-ICON | v0.9
PLASTIC-CPLA | HR | Dispose per local rules | PLASTIC-CPLA-ICON | v0.9
PLASTIC-CPLA | LT | Dispose per local rules | PLASTIC-CPLA-ICON | v0.9
PLASTIC-CPLA | LV | Dispose per local rules | PLASTIC-CPLA-ICON | v0.9
PLASTIC-CPLA | ET | Dispose per local rules | PLASTIC-CPLA-ICON | v0.9
PLASTIC-CPLA | MT | Dispose per local rules | PLASTIC-CPLA-ICON | v0.9
PLASTIC-CPLA | GA | Dispose per local rules | PLASTIC-CPLA-ICON | v0.9
PLASTIC-CPLA | SV | Dispose per local rules | PLASTIC-CPLA-ICON | v0.9
PLASTIC-CPLA | PT-BR | Dispose per local rules | PLASTIC-CPLA-ICON | v0.9